## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-UF-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1283 |  |  | Transmital Date: 17.Aug.2022
Document Title: Utility Flow Diagrams (UFD) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1283 |  |  | Transmital Date: 17.Aug.2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-UF-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به نهایی نشدن موضوع جابه‌جایی مخزن دیزل ژنراتور و عطف به نامه شماره 01/2294/249410 و نیاز به طرح موضوع مزبور از طریق رویه تغییرات و طرح در کمیته مربوطه مقرر گردد در این مدرک مطابق اسناد پیمان تهیه و تنظیم گردد ضمنا یکسان‌سازی با آخرین ویرایش مدارک پیش نیاز یا همنیاز از جمله P&ID ملاک عمل قرار گیرد. |  | 01/2294/281110 | 1401/08/03 | اعمال گردید.
2 | با توجه به حذف مخزن slug و تغییرات مربوطه ضروریست شماتیک، تجهیزات و محاسبات وابسته در نقشه اصلاح گردد. |  | 01/2294/281110 | 1401/08/03 | اصلاح گردید.
.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021