## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-SP-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1595 |  |  | Transmital Date: 22.Nov.2022
Document Title: Duty Specification for Instrument/Plant Air & Nitrogen Packages |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1595 |  |  | Transmital Date: 22.Nov.2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-SP-0002_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | میزان خلوص و دبی نیتروژن با موارد مندرج در مدارک مهندسی پایه متفاوت است. شایان ذکر است که نهايي سازي ميزان و مشخصات مورد نياز نيتروژن، پس از دريافت اطلاعات سازنده كمپرسور گاز امكان پذير خواهد بود. |  | BK-SUR-ENG-PCS-01-06369 | 07.Dec.2022 | باتوجه به مدذاکرات صورت گرفته با سازندگان کمپرسور، خلوض 98% مورد تایید آن سازنده می‌باشد. لازم به ذکر است دیتای مذکور در مدارک سازنده کمپرسور در مرحله‌ی طراحی تفضیلی پکیج کمپرسور فرآیندی ارائه خواهد شد. دبی در تمامی مدارک یکسان سازی شد و utility consumption سازنده به پیوست ارسال می‌گردد.
2 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-06369 | 07.Dec.2022 | اعمال می‌گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021