## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-PL-RT-0001_D04 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1517 |  |  | Transmital Date: 19/OCT/2022
Document Title: Pipeline Corrosion Study & Material Selection Report |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PL-TR-1517 |  |  | Transmital Date: 19/OCT/2022
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-PL-RT-0001_D04 |  |  | CRS Status: | C2
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به مفاد صورتجلسه مورخ 1401/05/12 (نامه شماره 179119 مورخ 1401/05/24) و با توجه به Note 1 مدرک نقطه نظر دیگری در خصوص حد مجاز خوردگی مطرح نمی باشد. پیرو تاکیدات این امور و با توجه به توصیه مشاور در مدرک و فرضیات پروژه (پیش بینی 40 درصد آب همراه ) ضروری است تمهیدات لازم جهت انجام توپکرانی دوره ای و در صورت نیاز به صورت منقطع پیش بینی و مدرک بر این اساس اصلاح و مجددا ارسال گردد. |  | 01/2291/329912 | 1401/09/06 | مدرک ویرایش گردید. پیشنهاد تمهید توپکرانی در مدرک ارائه شده است (صفحه 19 مدرک اشاره شده است). با این حال این پیشنهاد منوط به عملی بودن و امکان اجرایی شدن گشته است. مطابق بازدیدی میدانی این مشاور و نقطه نظرات بهره بردار در جلسه امکان اجرایی شدن چنین تمهیدی در طراحی فعلی وجود ندارد. لذا باقی تمهیدات پیش بینی شده در مدرک در ورودی خطو ط جریانی در واحد کلاستر در نظر گرفته شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri M.Hemmatikia | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 26/10/2022 |  |  |  |  | Date: 26/10/2022