## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-PL-RT-0001_D04 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1517 |  |  | Transmital Date: 19/OCT/2022
Document Title: Pipeline Corrosion Study & Material Selection Report |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PL-TR-1517 |  |  | Transmital Date: 19/OCT/2022
[5 empty] | CRS No: PEDCO-CRS-BK-SSGRL-PEDCO-110-PL-RT-0001_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در صفحه 19 در خصوص لزوم نصب CC و CP هم در ورودي خطوط لوله جرياني كه منظور Wellhead ها مي باشد و هم در خروچي كه منيفولد مي باشد صحبت شده است كه اين موضوع با اخرين ويرايش P&ID مربوط به Wellhead ها تطابق ندارد. مدرك P&IDهاي مربوط به Wellheadها و منيفولد با مدرك Pipeline Corrosion Study & Material Selection Report بايستي از اين نظر تطابق داشته باشند. لذا اصلاحات لازم بطور مطابق بايستي اعمال گردد. |  | BK-SUR-ENG-PPL-01-05978 | 2022-10-26 | در ورودی منیفولد اقلام پایش خوردگی در نظر گرفته شده است. مدرک مطالعات خوردگی بر این اساس ویرایش شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri M.Hemmatikia | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 26/10/2022 |  |  |  |  | Date: 26/10/2022