## Page 1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-PI-RT-0001-D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1521 |  |  | Transmital Date: 10/19/2022
Document Title: Piping Corrosion Study & Material Selection Report |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-1521 |  |  | Transmital Date: 10/19/2022
[5 empty] | CRS No:NISOC-CRS-BK-SSGRL-PEDCO-110-PI-RT-0001-D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص حد مجاز خوردگی برای بخش منیفولد همانگونه که قبلا ااعلام گردید در نتایج ارائه شده خوردگی حفره ای با ریسک بالا برای این بخش پیش بینی شده است که با توجه ب برش اب همراه به میزان 40 درصد و همچنین نقاط مرده در بخش منیفولد این موضوع نیاز به در نظر گرفتن تمهیدات لازم از جمله حد مجاز خوردگی مناسب جهت کنترل خوردگی دارد. در خصوص توضیحات مشاور مبنی بر این پروژه به صورت Extension منیفولد مجود می باشد نیاز به این توضیح می باشد اگر پروژه توسعه منیفولد موجود است ولی احداث خطوط درون منیفولد در برنامه کاری پیمانکار قرار دارد که در نظر گرفتن تمهیدات لازم جهت کنترل خوردگی این خطوط مطابق شرایط فرایندی ضروری می باشد. |  | 1401-2294-367496 | 1401/09/29 | در نتایج ارائه شده خوردگی حفره ای با ریسک بالا صرفا برای جریان های 1 و 2 (چاه018S منتهی به هدر موجود با 3 میلیمتر حد مجاز خوردگی) و 5 , 6 (چاه 008N) پیش بینی شده است. همچنین سرعت جریان در هدر بالا بوده و امکان تشکیل خوردگی حفره ای در عمل ناچیز است. با توجه به اینکه طراحی پایه حد مجاز خوردگی 3 میلی متر می باشد، جهت یکدست شدن طراحی و با در نظر گیری موارد بالا این پیمانکار همچنان حد مجاز 3 میلی متر را با رعایت انجام بازرسی های دوره ای کافی می داند. لازم به ذکر است درصورت اصرار کارفرمای محترم بر تغییر حدخوردگی مجاز (از 3 به 6 میلیمتر) ، علیرغم غیرضروری بودن آن، مراتب در قالب تغییرکاری مالی/زمانی قابل پیگیری می باشد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 09/06/2022 |  |  |  |  | Date: 09/06/2022