## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-SP-0009_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1481 |  |  | Transmital Date: 11/Oct/2022
Document Title: Specification for Overhead Traveling Cranes |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0109-ME-TR-1481 |  |  | Transmital Date: 11/Oct/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0009_D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ساختار وتعاریف مربوط به صفحه 4 مدرک مطابق با دیگر مدارک اصلاح گردد. |  | 01/2294/325717 | 1401/09/02 | نقطه نظر کارفرمای محترم اعمال گردید.
2 | بجای کلمه Company از کلمه Client استفاده گردد. |  | 01/2294/325717 | 1401/09/02 | کلمه Company بکار رفته در مدرک تنها مربوط به اسامی شرکت های مناطق نفت خیز جنوب یعنی National Iranian South Oilfields Company (NISOC) و پترو ایران Petro Iran Development Company (PEDCO) بوده که می بایست بطور کامل آورده شود.
3 | بخش 4 مطابق با دیگر مدارک تهیه گردد. |  | 01/2294/325717 | 1401/09/02 | مطابق نقطه نظر کارفرمای محترم اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: H. Adineh | Signature | M. Fakharian
| Date: |  |  |  |  | Date: 01/22/2023