## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-ME-DT-0001_D04 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1469 |  |  | Transmital Date: 09/Oct/2022
Document Title: Data Sheets For Oil Sump Pump - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0107-ME-TR-1469 |  |  | Transmital Date: 09/Oct/2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-ME-DT-0001_D03 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion | Clarification (By EPC Contractor)
| please change the type of pumps to VS4. and mentioned in a note, vendor can offer VS1 as an option. |  | BK-SUR-ENG-MEC-01-05922 | 2022-10-18 | According to the available head and capacity and also inquiries from vendors, the VS1 type can be supplied.
| MAWP for VS4 and OH are the same, please mention in a not the min acceptable hdrotest pressure shall not be less than 24 barg. |  | BK-SUR-ENG-MEC-01-05924 | 2022-10-18 | Noted, Note 32 will be revised accordingly.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.naserizadeh |  |  | Clarified By: H. Adineh | Signature | M. Fakharian
| Date:10/18/2022 |  |  |  |  | Date: 01/24/2023