## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-SP-0007_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1481 |  |  | Transmital Date: 11/Oct/2022
Document Title: Specification for Air Dryer Packages |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0109-ME-TR-1481 |  |  | Transmital Date: 11/Oct/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0007_D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | قسمت 5.6 صفحه 18 عبارت and proprietary microprocessor based حذف گردد. |  | 01/2294/325717 | 1401/09/02 | با توجه به روال طراحی سازندگان برای پکیج هوای ابزار دقیق شامل کمپرسور و درایر در پروژه های مشابه ، UCP اصلی برای پکیج کمپرسور با فرمت PLC Based در اتاق کنترل نصب میشود و سیستم درایر با توجه به ادوات به کار رفته در آن ، سیگنالهای انگشت شمار و لاجیک بسیار ساده ای که دارد با سیستم کنترل (UCP) غالبا Micro processor based نصب شده برروی اسکید،که به UCP اصلی پکیج هوا در اتاق کنترل مرتبط است کنترل میشود. این مطلب روال عادی طراحی سازندگان است و در بسیاری ازپروژه ها اعمال شده است که با P&ID پروژه همخوانی داشته و منافاتی با P&ID و Duty Spec طراحی پایه ندارد . لذا مدرک SPEC مربوط به این دو پکیج با توجه به توضیحات بالا اصلاح شده و جهت بررسی به کارفرمای محترم ارسال میگردد.
2 | ساختار و تعاریف مربوط به صفحه 4 مدرک مطابق با دیگر مدارک اصلاح گردد. |  | 01/2294/325717 | 1401/09/02 | مطابق نقطه نظر کارفرمای محترم اصلاح گردید.
3 | بجای کلمه Company از Client استفاده گردد. |  | 01/2294/325717 | 1401/09/02 | کلمه Company بکار رفته در مدرک مربوط به اسامی شرکت های مناطق نفت خیز جنوب و پترو ایران می باشد که می بایست بصورت کامل ذکر شود. National Iranian South Oilfields Company (NISOC) Petro Iran Development Company (PEDCO)
4 | - |  | - | - | مدرک Packing, Marking, Transportation Procedure با شماره BK-GNRAL-PEDCO-000-QC-PR-0045 به لیست مدارک پروژه بخش 3.3 اضافه گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: E. Sadeghi | Signature | M.Fakharian
| Date: |  |  |  |  | Date: 01/30/2023