## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-SP-0007_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1481 |  |  | Transmital Date: 11/Oct/2022
Document Title: Specification for Air Dryer Packages |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0006-ME-TR-1481 |  |  | Transmital Date: 11/Oct/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0007_D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | "The regeneration purge rate shall be automatically adjustable". Automatic adjustable purge rate is not feasible |  | BK-SUR-ENG-MEC-01-06072 | 2022-11-02 | Vendor will deviate if he can't follow this requirement and no more action is required.
2 | "The regeneration purge rate shall be automatically adjustable". Automatic adjustable purge rate is not feasible please clarify. |  | BK-SUR-ENG-MEC-01-06072 | 2022-11-02 | Vendor will deviate if he can't follow this requirement and no more action is required.
3 | "In the event of a power failure, the dryer shall continue to dry the incoming air to the specified dew point for a minimum of one hour." This time is not feasible for PSA dryers, please clarify. |  | BK-SUR-ENG-MEC-01-06072 | 2022-11-02 | Vendor will deviate if he can't follow this requirement and no more action is required.
4 | N2 pressurized purging for shipping to be added |  | BK-SUR-ENG-MEC-01-06072 | 2022-11-02 | As already mentioned in clause 8 of this specification, Preparation for packing and shipment of the equipment shall be in acc. with IPS-G-GN-210. Also as per project procedure (Packing, Marking, Transportation Procedure with Doc.No; BK-GNRAL-PEDCO-000-QC-PR-0045) there is no need to add N2 pressurized purging for shipping. Project requirements will be followed.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.BAVARSAD | Signature | H.naserizadeh |  |  | Clarified By: H. Adineh | Signature | M. Fakharian
| Date: 11/02/2022 |  |  |  |  | Date: 01/30/2023