## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W046S-PEDCO-110-HV-PY-0001-D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1441 |  |  | Transmital Date: 11/26/2022
Document Title:HVAC System Layout For Switchgear Building - W046S |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-HV-TR-1441 |  |  | Transmital Date: 11/26/2022
[5 empty] | CRS No: NISOC-CRS-BK-W046S-PEDCO-110-HV-PY-0001-D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بازگشت به نامه 13454(شماره وصول 244316)بررسی مدرک فوق منوط به نهایی شدن مدرک محاسبات است. |  | 01/2294/325652 | 1401/09/02 | مدرک محاسبات در تاریخ 1401/11/08 ارسال شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.naserizadeh |  |  | Clarified By: H. Adineh | Signature
| Date: 10/01/2022 |  |  |  |  | Date: 31/01/2023