## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W007S-PEDCO-110-PI-DW-0001_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1352 |  |  | Transmital Date: 10/4/2022
Document Title: Piping Plan Drawings- Extension of Binak B/C Mnifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-1352 |  |  | Transmital Date: 10/4/2022
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-PI-DW-0001_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | این مدرک می بایست بر اساس خروجی مدل سه بعدی تهیه گردد. لذا تا زمان نهایی نشدن مدل سه بعدی امکان اظهار نظر نهایی در این خصوص میسر نیست |  | 01/2294/307415 | 1401/08/21 | احتراما مدرک بر اساس آخرین وضعیت مدارک پایه فرایندی و مدل PDMS تهیه و به روز رسانی شده است و در صورت ایجاد تغییر روی مدارک پایه و مدل سه بعدی این مدرک نیز به روز رسانی خواهد شد.
2 | ارتفاع مندرج در یادداشت شماره 3 می بایست به نحوی در نظر گرفته شود که امکان دسترسی و انجام عملیات برای تمامی تجهیزات و شیرالات فراهم آید. |  | 01/2294/307415 | 1401/08/21 | احتراما تراز پلتفرم های دسترسی شیرالات بر مبنای این ارتفاع دیده شده است و امکان دسترسی شیرالات فراهم شده است
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri J.Mousazadeh | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature | M.Fakharian
| Date: 10/10/2022 |  |  |  |  | Date: 10/10/2022