## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W007S-PEDCO-110-PI-LI-0003-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1500 |  |  | Transmital Date:16-Oct-2022
Document Title: Piping Support List-Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-1500 |  |  | Transmital Date:16-Oct-2022
[5 empty] | CRS No:NISOC-CRS-W007S-PEDCO-110-PI-LI-0003-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدرک فوق پس از نهایی شدن مدل سه بعدی، نقشه های تکیه گاههای استاندارد و دیگر مدارک مربوطه تهیه گردد لذا از آنجا که تا کنون مدارک پیش گفته نهایی نشده اند، صحه گذاری و تایید این مدرک به لحاظ نوع و تعداد در شرایط کنونی از سوی این امور میسر نیست. لازم به ذکر است نوع تکیه گاه ها می بایست ضمن ارجاع به نقشه های استاندارد به مدارک پروژه نیز ارجاع گردد. از این رو نهایی سازی مدارک پیش نیاز نیز در اولویت کار تیم مهندسی آن پیمانکار قرار گیرد |  | 01/2294/290463 | 1401/08/10 | احتراما ساپورت های قسمت منیفولد به صورت اسپشیال ساپورت در واحد استراکچر طی مدرک BK-W007S-PEDCO-110-ST-DW-0001 و BK-W007S-PEDCO-110-ST-DW-0002 طراحی و اجرا می گردد. بنابراین در این مدرک ساپورت ها به صورت سازه موجود دیده شده و تگ استراکچر حذف گردید. تعداد و نوع مطابق آخرین مدرک استرس انالیز ارائه شده در این مدرک ارائه شده است. و در صورت به وجود آمدن هر گونه تغییری در مدارک پایه، این مدرک نیز به روز رسانی خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri J.Mousazadeh | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: |  |  |  |  | Date: