## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-TE-SP-0005_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0635 |  |  | Transmital Date: 08-04th-2021
Document Title: Specification For Telecommunication Tower |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-TE-TR-0635 |  |  | Transmital Date: 08-04th-2021
[5 empty] | CRS No: BK-GNRAL-NISOC-000-TE-SP-0005_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 3-1 نامه شماره 273260 ، به صفحه مسی به ابعاد 50X50 cm2 به همراه میله مسی در مدرک اشاره گردد. |  | 1400-2294-430784 | 1400-11-15 | اضافه شدن صفحه مسی با ابعاد 50 در50 برای سیستم ارت در نظر گرفته شد. شایان ذکر است با وجود صفحه مسی دیگر از میله راد استفاده نخواهد شد و این صفحه توسط هادی لخت و یا کابل به Earth Pit متصل خواهد شد.
2 | شماره گذاری F-Numbering مطابق نامه مربوطه انجام پذیرد. |  | 1400-2294-430784 | 1400-11-15 | شماره گذاری بر اساس استاندارد آن شرکت محترم و توافق صورتگرفته ارکان پروژه انجام شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: 08-08th-2021 |  |  |  |  | Date: