## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-PPL-PEDCO-320-PL-TB-0001-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1785 |  |  | Transmital Date:14-Jan-2023
Document Title: TBE For Line PIPE |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0110-PL-TR-1785 |  |  | Transmital Date:14-Jan-2023
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-PL-TB-0001-D00 |  |  | CRS Status: | C4
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدارک سازندگان ضمیمه ترنسمیتال ارسال نشده است و تنها جدول مقایسه سازندگان وجود دارد . لذا بررسی مدرک میسر نبوده واین ترانسمیتال عودت می گردد. |  | 01/2294/432552 | 1401/11/11 | احتراما مدارک سازندگان قبلا ضمیمه شده بود ولی سهوا ارسال نگردیده بود. علی ایحال مدارک مجددابه پیوست ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri J.Mousazadeh | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 25.Jan.2023 |  |  |  |  | Date: 25.Jan.2023