## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-ST-DW-0010-D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0911 |  |  | Transmital Date:5/8/2022
Document Title: Standard Drawing for Lighting pole foundation Plan & Details |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0010-ST-TR-0911 |  |  | Transmital Date: 5/8/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-ST-DW-0010_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1401-2294-63887 | 1401/02/26 | با توجه به موارد ذکر شده تیپ یک از نقشه فوق حذف و عنوان Lighting Tower در نظر گرفته شده است
2 |  |  | 1401-2294-63887 | 1401/02/26 | از نقشه استاندارد استفاده گردید
3 |  |  | 1401-2294-63887 | 1401/02/26 | از مدرک فوق استفاده گردید
4 |  |  | 1401-2294-63887 | 1401/02/26 | مدارک ذکر شده پس از مشخص شدن سازنده تهیه می گردد
5 |  |  | 1401-2294-63887 | 1401/02/26 | اضافه گردید
6 |  |  | 1401-2294-63887 | 1401/02/26 | جزییات مربوطه در مدارک حفاظت کاتدیک ارائه می گردد
7 |  |  | 1401-2294-63887 | 1401/02/26 | مطابق لیستوفر استاندارد اصلاح گردید
8 |  |  | 1401-2294-63887 | 1401/02/26 | به قسمت نوت مدرک اضافه گردید
9 |  |  | 1401-2294-63887 | 1401/02/26 | ضخامت توسط وندور ارائه می گردد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: