## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-LI-0004_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1282 |  |  | Transmital Date: 17 Aug 2022
Document Title: I/O List For F&G Systems - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1282 |  |  | Transmital Date: 17 Aug 2022
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-IN-LI-0004_D00 |  |  | CRS Status: | C3
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
3 | اظهار نظر در خصوص مدرک فوق ، منوط به نهایی شدن نقشه جانمایی سیستم اعلان حریق و سایر مدارک مرتبط می باشد. |  | 1401-2294-198406 | 1401/06/06 | مدرک مطابق آخرین نسخه از مدرک نقشه جانمایی، اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: