## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-GE-RT-0002-D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1563 |  |  | Transmital Date: 26/10/2022
Document Title: VALUE ENGINEERING STUDY ERPORT |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-GE-TR-1563 |  |  | Transmital Date: 10/26/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-GE-RT-0002-D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | درصفحه 92 ارسالی ، جدول 22 مطالب ارائه شده برای حذف پکیج متانول برای کاهش هزینه های بهره برداری عینا برای بهینه سازی سیتم لخته گیر ایستگاه ارائه شده است که می بایست مورد بررسی مجدد قرار گیرد. |  | 1401/2294/415500 | 1401/11/01 | بررسی و اصلاح گردید.
2 | با توجه به حذف پکیج متانول در ایستگاه جدید، پیمانکار می بایست گزارشی از وضعیت و ظرفیت پکیج متانول ایستگاه موجود و امکان جایگزینی را ارائه نماید. |  | 1401/2294/415500 | 1401/11/01 | گزارش درخواستی به پیوست این مدرک ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Maleki | Signature |  |  |  | Clarified By: | Signature
| Date: 16/11/2022 |  |  |  |  | Date: