## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-GE-RT-0002-D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1563 |  |  | Transmital Date: 26/10/2022
Document Title: VALUE ENGINEERING STUDY ERPORT |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-GE-TR-1563 |  |  | Transmital Date: 10/26/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-GE-RT-0002-D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | عطف به بند 4 صورتجلسه مورخه 1401/3/29، عبارت حذف پمپ Oil Sump Pit منيفولد بينك در صفحات قيد شده گزارش مذكور حذف گردد یا در صورت اصرار به حفظ آن به عدم پذیرش حذف پمپها در جلسه بررسی گزارش، اشاره گردد. |  | BK-SUR-ENG-GEN-01-06196 | 2022-11-16 | چون یکی از گزینه های مورد مطالعه می باشد ، ولی مورد تایید کارفرما قرار نگرفت، این مهم در صفحه 87 توضیح داده شده است.
2 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-GEN-01-06196 | 2022-11-16 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Maleki | Signature |  |  |  | Clarified By: | Signature
| Date: 16/11/2022 |  |  |  |  | Date: