## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DP-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0612 |  |  | Transmital Date: 20.Feb.2022
Document Title: Process & Utility Description |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0612 |  |  | Transmital Date: 20.Feb.2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-DP-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در بخش 2-4 فشار خروجی از ایستگاه تقویت فشار جدید بینک مطابق با مطالعات پایه نمی باشد اصلاح گردد. |  | 1400-2294-447187 | 1400/12/22 | مشخصات فرآیندی در بند 2-4 بر اساس آخرین توافقات صورت گرفته با آن کارفرمای محترم صورت پذیرفته است.
2 | در بخش 2-5 ماکزیمم ظرفیت PK-2203 با آخرین مدرک P&ID ارسالی مطابقت نداشته و نیاز به شفاف سازی می باشد. |  | 1400-2294-447187 | 1400/12/22 | اصلاح گردید.
3 | ضمن تکمیل لیست مدارک مرجع، توضیحات فرآیندی می‌بایست کامل و دقیق و با ذکر جزئیات، مراحل و تجهیزات باید و آنچه در حال حاظر در مدرک قید شده بخشی از مدرک Process Design Basis است. |  | 1400-2294-445277 | 1400/12/21 | اصلاح گردید.
4 | اطلاعات مربوط به پکیج هوا و نیتروژن می‌بایست اصلاح گردد. |  | 1400-2294-445277 | 1400/12/21 | اصلاح گردید.
.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021

## Sheet3
33.99