## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-LI-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1535 |  |  | Transmital Date: 10/23/2022
Document Title: Tie in List |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1535 |  |  | Transmital Date: 10/23/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0003_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | برخی از شماره خطوط درج شده در مدرک با آخرین ویرایش مدرک P&ID همخوان نبوده و ضروریست یکسان سازی گردد به عنوان مثال در TP-01 شماره خط ذکر شده با مدرک P&ID یکسان نمی باشد. |  | 1401-2294-323246 | 1401/09/01 | بررسی شده و اصلاحات لازم صورت گرفته است.
2 | همانطور که در نامه پسشین این امور به شماره1400/2294/443237 مورخ 19/12/1400 عنوان گردید ضروریست فشارهای طراحی درج شده در مدرک اصلاح گردد. |  | 1401-2294-323246 | 1401/09/01 | اعمال گردید.
2 | توضیحات ارایه شده ذیل Note1 مورد قبول نمی باشد. و ضروری است در این مقطع از پروژه این اطلاعات توسط پیمانکار نهایی گردد. |  | 1401-2294-323246 | 1401/09/01 | تمامی توضیخات ارائه شده ذیل NOTE 1 تکمیل گردید به استثنا TIE-IN خط FROM SLUG PUMPS TO EXISTING 4 INCH PIPELINE که توسط کارفرمای محترم اجرا شده است و بر اساس استعلام صورت گرفته از سایت موجود بینک، خط لوله فوق شماره خط ندارد. لذا خواهشمند است آن کارفرمای محترم اطلاعات خط مذکور را جهت تکمیل مدرک فوق در اختیار این پیمانکار قرار دهد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: