## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-LI-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1535 |  |  | Transmital Date: 10/23/2022
Document Title: Tie in List |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1535 |  |  | Transmital Date: 10/23/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0003_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نوع اتصال (فلنج یا جوش) در بسیاری از Tie-In ها نیاز به بازنگری دارد. به عنوان نمونه Tie-inهای شماره7،9، 11 و 12 می بایست به صورت Weld در نظر گرفته شوند. |  | BK-SUR-ENG-PCS-01-06112 | 2022-11-07 | در نقاط Tie in می بایست خط مورد نظر در ورودی و یا خروجی از Battery Limit محدوده شرح خدمات ایستگاه تقویت فشار به صورت فلنجی به این پیمانکار تحویل داه شود.
2 | Tie-in شماره 9 به صورت UG در نظر گرفته شود. |  | BK-SUR-ENG-PCS-01-06112 | 2022-11-07 | اعمال گردید.
3 | موارد HOLD مربوط به Tie-in شماره 12 می بایست در بازدید از سایت برداشت شود. (سایز خط و فشار عملیاتی پمپ تزریق متانول) |  | BK-SUR-ENG-PCS-01-06112 | 2022-11-07 | اعمال گردید.
4 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-06112 | 2022-11-07 | اعمال می گردد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Faramarzpour | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: