## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W028-PEDCO-110-PI-DW-0001-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0533 |  |  | Transmital Date: 02-Feb-2022
Document Title:Plot Plan Drawing - W028 |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-0533 |  |  | Transmital Date:
[5 empty] | CRS No: CRS-BK-W028-PEDCO-110-PI-DW-0001-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظرات بصورت مارك شده در مدرك به پيوست ارسال مي گردد. كامنتهاي كلي مشابه كامنتهاي ارسال شده بر مدرك ترانسميتال T-0526 مربوط به چاه W018S مي باشد. پيمانكار تا زمان نهايي نشدن نقشه Plot Plan چاه هاي W018S و W028 از ارسال نقشه چاههاي ديگر خودداري نمايد. |  | BK-SUR-ENG-PIP-00-03123 | 19-Feb.-2022 | احتراما پاسخ نقطه نظرات به پیوست ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri G.Khosravizadegan | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 19-Feb.-2022 |  |  |  |  | Date: 19-Feb.-2022