## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W028S-PEDCO-110-PI-MT-0002_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1352 |  |  | Transmital Date: 04/Sep/2022
Document Title: MTO FOR FITTINGS – W028S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-PI-TR-1352 |  |  | Transmital Date: 04/Sep/2022
[5 empty] | CRS No: CRS-BK-W028-PEDCO-110-PI-MT-0002_D02 |  |  | CRS Status: | C2
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظر به اينكه هنوز P&ID و مدل سه بعدي سرچاهي پروژه نهايي نشده است و PMS پروژه هنوز مورد تأييد قرار نگرفته است و با توجه به كامنتهاي قبلي در مدل سه بعدي هنوز ايرادات زير در MTO مشاهده مي گردد لذا مدرك مورد تأييد نبوده و پس از تأييد P&ID و PMS پروژه و ارسال مدل سه بعدي نهايي سرچاهي بايستي MTO مجدداً ارسال گردد. |  | BK-SUR-ENG-PIP-01-05622 | 2022-09-10 | احتراما موارد ابهامات باقی مانده در خصوص مدارک P&ID در جلسه مورخ 1401/11/11 نهایی گردیده است.
2 | در مدرك MTO آيتم 5 به Latrolet اشاره گرديده است. كاربرد آن در كجاست؟ |  | BK-SUR-ENG-PIP-01-05622 | 2022-09-10 | در ویرایش D03 مدرک آیتم مذکور حذف گردیده است.
3 | اتصال SC قبل از Stone Trap ديده نشده است. |  | BK-SUR-ENG-PIP-01-05622 | 2022-09-10 | در ویرایش D03 مدرک لحاظ گردیده است.
4 | براي اتصال انشعاب TG آيتم 6 قطعه Weldolet 6x 1 1/2 در نظر گرفته شده است در حاليكه مطابق PMS پروژه Sockolet در نظر گرفته مي شود. |  | BK-SUR-ENG-PIP-01-05622 | 2022-09-10 | مطابق مدرک S5L-9002 می بایست از اتصال Weldolet استفاده گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: J.Mousazadeh | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 10/09/2022 |  |  |  |  | Date: 10/09/2022