## PEDCO
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-DG-0009_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1302 |  |  | Transmital Date: 22 Aug 2022
Document Title: Instrument & F&G Junction Box Termination Diagram - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: |  |  | Transmital Date: 22 Aug 2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-IN-DG-0009_D01 |  |  | CRS Status: | C2
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  |  | 2022-09-04 | -
2 | با توجه به اينكه مدارك پيش نياز مانند I/O نهايي نيست در صورت هر گونه تغيير موارد در اين مدرك منعكس گردد. |  |  | 2022-09-04 | مدرک حاضر با آخرین مدارک مرجع بروز رسانی شده است
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 4 Sep 2022 |  |  |  |  | Date:

## NISOC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-DG-0009_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1302 |  |  | Transmital Date: 22 Aug 2022
Document Title: Instrument & F&G Junction Box Termination Diagram - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-1302 |  |  | Transmital Date: 22 Aug 2022
[5 empty] | CRS No:NISOC-CRS-BK-W007S-PEDCO-110-IN-DG-0009_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
2 | در خصوص مورد 2 از RELAY SHEET با توجه به عنوان مدرک لازم است سیگنال / ترمینیشن مربوط به سیستم F&G نمایش داده شود با در نظر گرفتن تجهیزات F&g برای ساختمان های واحد کلاستر بیتک چرا از JB استغاده نمی گردد |  | 01/2294/240318 | 1401/07/06 | ساختمان های واحد کلاستر بینک در تعهد پیمانکار نمی باشد . سیگنال های F&G ( طراحی شده ) ساختمان کنترل موجود به FACP مستقیم ارسال می شوند ( مدرک اصلاح گردید )
2 | در خصوص مورد 4 از RELAY SHEET با نوجه به انکان ترتیب انتخاب سیگتال های جریان و سطح بصورت ترم افزاری تظر خاصی مطرح نمی باشد |  | 01/2294/240318 | 1401/07/06 | -
2 | در خصوص بقیه موارد از RELAY SHEET تظر خاصی مطرح نمی باشد |  | 01/2294/240318 | 1401/07/06 | -
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 4 Sep 2022 |  |  |  |  | Date: