## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W028S-PEDCO-110-PI-MT-0003_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1352 |  |  | Transmital Date:04/Sep/2022
Document Title: MTO For Flanges - W028S |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0106-PI-TR-1352 |  |  | Transmital Date:04/Sep/2022
[5 empty] | CRS No: CRS-BK-W028S-PEDCO-110-PI-MT-0003_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظر به اينكه هنوز P&ID و مدل سه بعدي سرچاهي پروژه نهايي نشده است و PMS پروژه هنوز مورد تأييد قرار نگرفته است لذا مدرك مورد تأييد نبوده و پس از تأييد P&ID و PMS پروژه و ارسال مدل سه بعدي نهايي سرچاهي بايستي MTO مجدداً ارسال گردد. |  | BK-SUR-ENG-PIP-01-05622 | 2022-09-10 | احتراما موارد ابهامات باقی مانده در خصوص مدارک P&ID در جلسه مورخ 1401/11/11 نهایی گردیده است.
2 | تعداد فلنج هاي آيتم 3 و آيتم 5 بررسي گردد. بنظر مي رسد تعداد فلنج هاي آيتم 3 و 5 بايستي براي هر دو 3 عدد باشد. |  | BK-SUR-ENG-PIP-01-05622 | 2022-09-10 | در ویرایش D03 مدرک شاهد تغییرات هستیم.
3 | ضخامت فلنج آيتم 5 كمتر از ضخامت مطابق استاندارد API 6A نباشد. ضخامت استاندارد فلنج 6 اينچ كلاس API 3000 معادل 10.6mm مي باشد. |  | BK-SUR-ENG-PIP-01-05622 | 2022-09-10 | مطابق ویرایش D03 مدرک بررسی گردد.
4 | بنظر مي رسد فلنج آيتم 4 كه به لوله كلاس AN15 متصل مي گردد بايستي داراي ضخامت معادل آن باشد ولي از آنجا كه ضخامت فلنج هاي API 6A نبايستي كمتر از ضخامت استاندارد باشد بهتر است براي آن ضخامت 8.15mm در نظر گرفته شود. |  | BK-SUR-ENG-PIP-01-05622 | 2022-09-10 | مطابق ویرایش D03 مدرک بررسی گردد.
5 | بهتر است سايز كليه فلنج هاي مطابق API 6A بر اساس سايزهاي آن استاندارد ذكر گردد. |  | BK-SUR-ENG-PIP-01-05622 | 2022-09-10 | در مدارک پیشنهادی سازندگان اعلام خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: J.Mousazadeh | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 10/09/2022 |  |  |  |  | Date: 10/09/2022