## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PR-DP-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0990 |  |  | Transmital Date: 5/22/2022
Document Title: Process Description |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0990 |  |  | Transmital Date: 5/22/2022
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-PR-DP-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | دبی پمپ های ارسال مایعات اصلاح گردد . |  | 1401-2294-104506 | 1401/03/25 | دبی نرمال پمپ ارسال مایعات در بند 4.1.2 ذکر شده است. لازم به ذکر است دبی در شرایط استاندارد بر اساس آخرین ویرایش مدرک PFD اصلاح گردید.
2 | به موجود بودن خط 4 اینچ اشاره شود |  | 1401-2294-104506 | 1401/03/25 | اعمال گردید.
3 | فشار پمپ های ارسال میعانات بیان گردد. |  | 1401-2294-104506 | 1401/03/25 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021