## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK14-PEDCO-110-CV-PY-0001 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-1614 |  |  | Transmital Date: 27-Nov-2022
Document Title : General Civil Layout - BK14 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0001-CV-T-1614 |  |  | Transmital Date: 27-Nov-2022
[5 empty] | CRS No: NISOC-CRS-BK-GNRAL-PEDCO-110-CV-PY-0005-D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در پاسخ به ردیف 3 از Clarification By EPC Contractor تا هنگام تصویب Plot Plan مصوب، نامه شماره 284599 بر قوت خود باقی است. |  | 01-2294-362006 | 1401/09/26 | مدرک حاضر بر اساس آخرین تغییرات پلات پلن در جلسات بررسی مدل سه بعدی، تهیه گردیده است.
2 | در پاسخ به ردیف 4 از Clarification By EPC Contractor هرگونه اقدام در چارچوب اسناد و مدارک پیمان مورد نظر این امور می باشد و بابت انجام هر فعالیت خارج از شرح قرارداد با مسئولیت آن پیمانکار بوده و هیچگونه بهایی پرداخت نخواهد شد. |  | 01-2294-362006 | 1401/09/26 | مورد قبول می باشد.
3 | در پاسخ به ردیف 6 از Clarification By EPC Contractor به بند یک(بالا) مراجعه و ملاک عمل خواهد بود. |  | 01-2294-362006 | 1401/09/26 | مدرک حاضر بر اساس آخرین تغییرات پلات پلن در جلسات بررسی مدل سه بعدی، تهیه گردیده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: