## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-LI-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0888 |  |  | Transmital Date: 01 May 2022
Document Title: Instrument Index |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR- 0888 |  |  | Transmital Date: 01 May 2022
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-IN-LI-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Note 4 اصلاح گردد ; جهت ESDV-3202 سیستم ESD جدید طراحی و اجرا میگردد. |  | 01/2294/65632 | 1401/02/27 | با توجه به شرح کار پروژه، آخرین نسخه مدرک های Instrument & Control System Design Criteria ،Block Diagram Configuration For Control/ESD/F&G System ، شیر ESDV-3202 مجددا خریداری شده اما به سیستم کنترل/ESD موجود متصل میشود.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: