## NISOC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-LI-0009_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1303 |  |  | Transmital Date: 22 Aug 2022
Document Title: Instrument /F&G Cable List - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1303 |  |  | Transmital Date: 22 Aug 2022
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-IN-LI-0009_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | سیگنال های سطح ( level ) موجود در لیست آورده شود |  | 01/2294/240271 | 1401/07/06 | همه سیگنال های موجود در لیست I/O در این مدرک لحاظ شده است
2 | با توجه به اینکه برای ساختمان های موجود واحد کلاستر بینک بایستی تجهیزات f&g در نظر گرفت این مدرک پس از نهای شدن نقشه جانمایی تجهیزات F&G مورد بازتگری قرار گیرد و برای این امور ارسال گردد |  | 01/2294/240271 | 1401/07/06 | ساختمان های دیگر واحد کلاستر در تعهد این پیمانکار نمی باشد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 3 Oct 2022 |  |  |  |  | Date: