## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-LI-0009_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1303 |  |  | Transmital Date: 22 Aug 2022
Document Title: Instrument /F&G Cable List - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1303 |  |  | Transmital Date: 22 Aug 2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-IN-LI-0009_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-05597 | 2022-09-04 | ملاحظه شد.
2 | با توجه به اينكه مدارك پيش نياز مانند I/O نهايي نيست در صورت هر گونه تغيير موارد در اين مدرك منعكس گردد. |  | BK-SUR-ENG-INS-01-05597 | 2022-09-04 | مدرک مطابق آخرین اصلاحات در مدارک مرجع به روز رسانی گردید.
3 | مدرك مورد نظر با I/O تطابق ندارد براي مثال سيگنال XST-1702 حذف گردد. موارد مجدد بررسي و ارائه گردد. |  | BK-SUR-ENG-INS-01-05597 | 2022-09-04 | مدرک مطابق آخرین اصلاحات در مدارک مرجع به روز رسانی گردید.
4 | سطر 52 بر اساس I/O اصلاح شود. |  | BK-SUR-ENG-INS-01-05597 | 2022-09-04 | مدرک مطابق آخرین اصلاحات در مدارک مرجع به روز رسانی گردید.
5 | ارتباط سريال بين سيستم ESD /FACP و ESD در مدرك ديده شود. |  | BK-SUR-ENG-INS-01-05597 | 2022-09-04 | اضافه شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 4 Sep 2022 |  |  |  |  | Date: