## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK14-PEDCO-110-CV-PY-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1623 |  |  | Transmital Date: 27 Nov 2022
Document Title: Rough Grading Plans -BK14 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-T-1623 |  |  | Transmital Date: 27 Nov 2022
[5 empty] | CRS No: NISOC-CRS-BK-BK14-PEDCO-110-CV-PY-0003-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در پاسخ به بند یک از Clarification (By EPC Contractor) به آگاهی می رساند سازمان کارفرما جهت تسهیل روند پروژه نهایت همکاری را از خود نشان داده و آن پیمانکار نیز موظف به رعایت تمامی رویه های جاری می باشد. توضیحات و ایرادات گفته شده توسط این امور در راستای رعایت اصول حرفه ای تولید نقشه های مهندسی و ممانعت از دوباره کاری های بعدی است. |  | 01-2294-363065 | 1401/9/27 | مورد قبول است.
2 | از نظر این امور ارسال همزمان مدارک مانعی ندارد لیکن پیش نیاز این مدرک و مدرک General Civil layout مدرک پلات پلان است که تاکنون توسط پیمانکار تهیه و ارائه نشده لذا همانگونه که در بند 3 از نامه شماره 296858 نیز اعلام گردید، ابتدا می بایست مدرک Plot plan- بعنوان پیش نیاز- برای چاه های دارای تلمبه یدک مصوب شود سپس مدارک بعدی تولید گردد که تاکنون مستندات خواسته شده دریافت نشده و امکان بررسی این مدرک در این مرحله نیز مقدور نیست. |  | 01-2294-363065 | 1401/9/27 | مدرک حاضر بر اساس آخرین تغییرات پلات پلن در جلسات بررسی مدل سه بعدی، تهیه گردیده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: