## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0029_D05 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1683 |  |  | Transmital Date: 11/Dec/2022
Document Title: Mechanical Data Sheets For Fire Water Main Pump-Elect.Motor Driven |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0111-ME-TR-1683 |  |  | Transmital Date: 11/Dec/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0029_D04 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص مدرک فوق میزان بیشینه رطوبت ذکر شده در مدرک با Process Basis of Design پروژه همخوان نبوده ضروریست یکسان سازی گردد. |  | 01/2294/423374 | 1401/11/05 | نقطه نظر کارفرمای محترم اعمال می گردد.
2 | با توجه به نهایی سازی مدرک Process design of Design ضروریست شرایط ذکر شده در این مدرک در داده برگه درج گردد |  | 01/2294/423374 | 1401/11/05 | نقطه نظر کارفرمای محترم اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: H. Adineh | Signature | M. Fakharian
| Date: |  |  |  |  | Date:02/15/2023