## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-PY-0007 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1117 |  |  | Transmital Date: Jun-25th-2022
Document Title: CCTV Equipment Layout for GCS Area |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0104-IN-TR-1117 |  |  | Transmital Date: Jun-25th-2022
[5 empty] | CRS No: CRS-BK-GCS-PEDCO-120-IN-PY-0007_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نقشه مطابق آخرين ويرايش Unit Plot Plan باشد. مطابق با شرح كار، طراحي و ساخت CCTV Control Room در محدوه كاري پيمانكار مي باشد لذا جانمايي آن بايستي در Plot plan و جنب درب ورودی کارخانه تقویت فشار گاز بینک نشان داده شود. |  | BK-SUR-ENG-INS-01-05266 | Jul-11th-2022 | مدرک بر اساس آخرین پلات پلن مورد ویرایش قرار گرفته است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: AP.Golrang , S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: Jul-11th-2022 |  |  |  |  | Date: