## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-DT-0001_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1086 |  |  | Transmital Date: 18/JUN/2022
Document Title: Data Sheets For Strainers |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0103-PI-TR-1086 |  |  | Transmital Date: 18/JUN/2022
[5 empty] | CRS No: CRS-BK-GCS-PEDCO-120-PI-DT-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | اطلاعات فرایندی مطابق با اخرین تغییرات در مدرک مندرج گردد. |  | 01/2294/156732 | 1401/05/05 | احتراما نقطه نظرات مربوطه در ویرایش D01 مدرک اعمال گردید.
2 | با توجه به عدم تایید مطالعات خوردگی، در خصوص جنس کالا نمی توان اظهار نظر نمود. |  | 01/2294/156732 | 1401/05/05 | احتراما در این مقطع زمانی ابهامات مربوطه رفع گردیده و مدرک مربوط به خوردگی نهایی گردیده است.
3 | فشار تست هیدرواستاتیک مطابق با کد طراحی در مدرک درج گردد. |  | 01/2294/156732 | 1401/05/05 | احتراما نقطه نظرات مربوطه در ویرایش D01 مدرک اعمال گردید.
4 | پیشنهاد می گردد در بخش یادداشتها شماره نقشه های استاندارد مربوطه به عنوان راهنما در مدرک درج گردد. |  | 01/2294/156732 | 1401/05/05 | احتراما نقطه نظرات مربوطه در ویرایش D01 مدرک اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 03/07/2022 |  |  |  |  | Date: 03/07/2022