## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PR-CE-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1053 |  |  | Transmital Date: 6/11/2022
Document Title: Cause & Effect Diagram |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1053 |  |  | Transmital Date: 6/11/2022
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-PR-CE-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نقطه نظرات ارائه شده بر مدرك فلسفه توقف اضطراري و نيز موارد عنوان شده در جلسه HAZOP در اين مدرك نيز اعمال گردد. |  | BK-SUR-ENG-PCS-01-04989 | 2022-07-05 | اعمال گردید.
2 | توضيحات نوشته شده براي شير هاي ESDV نياز به بازنگري دارد. |  | BK-SUR-ENG-PCS-01-04989 | 2022-07-05 | اصلاح گردید.
3 | در نظر گرفتن سطح صفر براي علت هاي ذكر شده قابل قبول نبوده و نياز به بازنگري دارد. |  | BK-SUR-ENG-PCS-01-04989 | 2022-07-05 | مورد بازنگری قرار گرفته و به سطح 1 انقتقال داده شده است.
4 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-04989 | 2022-07-05 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: