## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PR-PH-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1751 |  |  | Transmital Date: 1/1/2023
Document Title: ESD Philosophy |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-01751 |  |  | Transmital Date: 1/1/2023
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-PR-PH-0005_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
9 | نظری مطرح نمی باشد و صرفا لازم است نقطه نظرات ذينفع اصلي اعمال گردد .شایان ذکر است که مطابق شرایط عمومی پیمان فی ما بین و با توجه به مسئولیتهای مالی-قراردادی پیمانکار، مسئولیت بروز هرگونه اشتباه و تناقض، کمبود اسناد و مدارک فنی و اطلاعات تهیه شده از سوی پیمانکار اعم از اینکه از سوی کارفرما تایید شده و یا نشده باشد بر عهده پیمانکار است. |  | BK-SUR-ENG-PCS-01-06703 | 2023-01-18 | اعمال می‌گردد. لازم به ذکر است مدرک فوق بر اساس آخرین تغییرات مدرک ESD BLOCK DIAGRAM به شماره مدرک "BK-PPL-PEDCO-320-PR-BD-0001" بر روز رسانی گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: