## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-EL-PY-0003_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0898 |  |  | Transmital Date: 02-May-2022
Document Title: Layout For Cathodic Protection System for Siahmakan Gas Injection |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0102-EL-TR-0898 |  |  | Transmital Date: 02-May-2022
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-EL-PY-0003_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در جانمایی ارسالی دو ایستگاه حفاظت کاتدی مشخص شده است، در صورتیکه بر اساس مدارک طراحی تعداد ایستگاهههای حفاظت کاتدی 3 عدد می باشد. |  | 1401-2294-85151 | 1401-03-10 | بر اساس مدرک محاسباتی که با تراسنمیتال شماره 1845 ارسال شده است، تعداد ایستگاهها 2 عدد در نظر گرفته شده است.
2 | در جانمایی سامانه حفاظت کاتدی، بسترهای مجاور، خطوط لوله متقاطع، حوضچه های موجود در مسیر، تقاطع با کابلهای فشارقوی، تقاطع لوله با جاده و غیر مشخص گردد. |  | 1401-2294-85151 | 1401-03-10 | مدرک Plan & Profile خط لوله به عنوان پیوست اضافه گردید که در آن بسترهای مجاور، خطوط لوله متقاطع، حوضچه های موجود در مسیر و . . . مشخص شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 15-May-22 |  |  |  |  | Date: