## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-LI-0002_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1105 |  |  | Transmital Date: 21 Jun 2022
Document Title: I/O List For Control /ESD System |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1105 |  |  | Transmital Date: 21 Jun 2022
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-IN-LI-0002_D00 |  |  | CRS Status: | C3
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | صفحه 6 شماره NOTE ها در قسمت REMARKS اصلاح گردد. |  | 01/2294/213364 | 1401/6/15 | با توجه به کامنت کارفرمای محترم، شماره NOTES اصلاح گردید.
2 | صفحه 6 توضیح NOTE6 صحیح نمی باشد، تجهیزات توقف / کنترلی جدید در پنل موجود نصب میشوند. سیگنال های کنترلی و ESD بایستی مجزا در نظر گرفته شوند، با توجه به این موضوع کل مدرک مورد بازنگری قرار گیرد. |  | 01/2294/213364 | 1401/6/15 | مطابق کامنت کارفرمای محترم و با توجه به آخرین بازدید ها ، NOTE6 صفحه 6 اصلاح گردید.
3 | مدرک با توجه به تغییرات در نقشه های P&ID و مدارک مرتبط بروزرسانی گردد. |  | 01/2294/213364 | 1401/6/15 | با توجه به کامنت کارفرمای محترم و آخرین نسخه P&ID و مدارک مرتبط ، مدرک اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: