## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-LI-0002_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1105 |  |  | Transmital Date: 21 Jun 2022
Document Title: I/O List For Control /ESD System |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1105 |  |  | Transmital Date: 21 Jun 2022
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-IN-LI-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدارك مربوط به سيستم كنترل و ESD بصورت مشترك ارائه شده است (I/O ليست) ، اين درحاليست كه در رويژن هاي پيشين مربوط به MDL، مدارك بصورت مجزا ارائه شده است و ارائه مدارك بصورت مشترك روال تاييد شده اي نمي باشد. |  | BK-SUR-ENG-INS-01-05000 | 2022-07-05 | مطابق بازدید انجام شده و با توجه به I/O های اندک شمار آن ، MDL اصلاح شد و بالطبع مدرک نیز متناسب با آن ارائه شده است.
2 | موارد با توجه به آخرين تغييرات P&ID نهايي و اعمال گردد. |  | BK-SUR-ENG-INS-01-05000 | 2022-07-05 | با توجه به کامنت کارفرمای محترم و آخرین نسخه P&ID ، مدرک اصلاح گردید.
3 | Note-4 اصلاح گردد. به سيستم كنترل جديد متصل مي شوند. |  | BK-SUR-ENG-INS-01-05000 | 2022-07-05 | با توجه به کامنت کارفرمای محترم، NOTE4 اصلاح گردید.
4 | سيگنالهاي مربوط به سيستم كنترل تقويت فشار گازي در I/O List مربوطه نيز ديده شود. |  | BK-SUR-ENG-INS-01-05000 | 2022-07-05 | سیگنال های مربوط به سیستم کنترل GCS هم در صفحه 5 و هم در صفحه 4 بخش ابتدایی SUMMARY به وضوح دیده شده است .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 5 July 2022 |  |  |  |  | Date: