## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0013_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1376 |  |  | Transmital Date: 07-Sep- 2022
Document Title: PMR FOR OVERHEAD TRAVELLING CRANES |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-ME-TR-1376 |  |  | Transmital Date: 07-Sep- 2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0013_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ساختار کلی مدرک مورد تایید بوده ولیکن ارسال نسخه بعدی این مدرک منوط به نهایی سازی مدارک مرتبطه مهندسی و درج نسخ تایید شده در مدارک فوق الذکر می باشد. معذالک جهت پرهیز از مکاتبات مضاعف و تسریع در تایید مدارک فوق، نهایی سازی مدارک پیشنیاز در دستور کار تیم مهندسی آن پیمانکار قرار گیرد. |  | 01/2294/231584 | 1401/06/29 | با توجه به نهایی شدن اکثر مدارک پیوست خواهشمند است بررسی مدرک در دستور کار آن کارفرمای محترم قرار گیرد. همچنین در صفحه 8 از 23 ، QA organization به QA/QC organization chart اصلاح ، در صفحه 9 از 23 دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات به شماره مدرك ICE-EID-MI-SP02-REV-01 اضافه و همچنین در صفحه 21 از 23 یادداشت List of Documents will be Finalized in VPIS اضافه گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M. Torkaman P.Bavarsad | Signature | H.Naserizadeh |  |  | Clarified By: H. Adineh | Signature | M. Fakharian
| Date: 24/09/2022 |  |  |  |  | Date: 02/21/2023