## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0013_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1376 |  |  | Transmital Date: 07-Sep- 2022
Document Title: PMR FOR OVERHEAD TRAVELLING CRANES |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0107-ME-TR-1376 |  |  | Transmital Date: 07-Sep- 2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0013_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در بند 5.1.1، عبارت "QA Organization" به "QA/QC Organization Chart" تغيير يابد. |  | BK-SUR-ENG-MEC-01-05751 | 2022-09-24 | Noted
2 | در بند 6: 1-عبارت "Project ITP Procedure" به "Commodity Procurement and Manufacturing Inspection Instruction" تغيير يابد. 2-دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات به شماره مدرك ICE-EID-MI-SP02-REV-01 اضافه گردد. |  | BK-SUR-ENG-MEC-01-05751 | 2022-09-24 | Noted
3 | در جدول بند 11.2: -در رديف 1، عبارت "See Attachment 2" حذف گردد. - عبارت "List of Documents will be Finalized in VPIS" در نوتها اضافه گردد. |  | BK-SUR-ENG-MEC-01-05751 | 2022-09-24 | Noted
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M. Torkaman P.Bavarsad | Signature | H.Naserizadeh |  |  | Clarified By: H. Adineh | Signature | M. Fakharian
| Date: 24/09/2022 |  |  |  |  | Date: 02/21/2023