## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-LI-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1425 |  |  | Transmital Date: 20 Sep 2022
Document Title: Instrument Index |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1425 |  |  | Transmital Date: 20 Sep 2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بين اين مدرك و مدرك مرجع PID تناقض وجود دارد. در زير بعضي از آنها بعنوان نمونه آورده شده است. موارد مجددا بررسي و اصلاح گردد. |  | BK-SUR-ENG-INS-01-05864 | 2022-10-09 | اصلاح شد.
2 | ادواتي مانند CC-2150 و CP-2151 در نقشه شماره BK-GCS-PEDCO-120-PR-PI-0013 (1 of 3) در ليست موجود نمي باشد. |  | BK-SUR-ENG-INS-01-05864 | 2022-10-09 | اصلاح شد.
3 | مدرك ارائه شده با PID تناقض دارد براي مثال TSV-2281A در مدرك وجود ندارد. |  | BK-SUR-ENG-INS-01-05864 | 2022-10-09 | در PID-23 ، ولو TSV-2281 موجود می باشد که در این مدرک آورده شده است.
4 | بين اين مدرك و PID تناقض وجود دارد براي مثال PG-2162 در BK-GCS-PEDCO-120-PR-PI-0014 |  | BK-SUR-ENG-INS-01-05864 | 2022-10-09 | اصلاح شد.
5 | بين اين مدرك و PID تناقض وجود دارد براي مثال ESOV-2201 در نقشه BK-GCS -PEDCO-120-PR-PI-0015 |  | BK-SUR-ENG-INS-01-05864 | 2022-10-09 | اصلاح شد.
6 | بين اين مدرك و PID تناقض وجود دارد براي مثال PIT-2151 در BK-GCS-PEDCO-120-PR-PI-0016 |  | BK-SUR-ENG-INS-01-05864 | 2022-10-09 | در این PID ، تگ PIT-2151 وجود ندارد.
7 | موارد Duplicate اصلاح گردد. مانند PIT-2112 |  | BK-SUR-ENG-INS-01-05864 | 2022-10-09 | اصلاح شد.
8 | Type مربوط به ادوات LT در قسمت توضيحات اضافه گردد. |  | BK-SUR-ENG-INS-01-05864 | 2022-10-09 | اصلاح و اضافه شد.
9
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 9 Oct 2022 |  |  |  |  | Date: