## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-SSGRL-PEDCO-110-AR-DW-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1499 |  |  | Transmital Date:1401/07/23
Document TitleArchitectural Drawing For Fire Shed |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-AR-T-1499 |  |  | Transmital Date:1401/07/23
[5 empty] | CRS No: NISOC-CRS-BK-SSGRAL-PEDCO-110-AR-DW-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | رقوم 0.00 نمایش داده شده با عنوان H.H.P صحیح نیست رقوم مذکور به H.P.G اصلاح گردد. |  | 1401-2249-294220 | 1401/08/12 | اعمال گردید.
2 | شیب بندی سقف بازنگری گردد با شیب در نظر گرفته شده محل ریزش آب باران در محل ورودی قرار گرفته است که صحیح نیست. |  | 1401-2249-294220 | 1401/08/12 | اعمال گردید.
3 | نمایش و ترسیم سکشنها و نماها ناقص است،بازنگری و اصلاح گردد. |  | 1401-2249-294220 | 1401/08/12 | اعمال گردید.
13 | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
14
15 | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
16 | Commented By: | Signature |  |  |  | Clarified By: | Signature
17
18 | Date: |  |  |  |  | Date:
17
18
19
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
Legend
Signature