## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK14-PEDCO-110-PI- PY -0001_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1628 |  |  | Transmital Date: 11/28/2022
Document Title: Plot Plan Drawing - BK14 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-1628 |  |  | Transmital Date: 11/28/2022
[5 empty] | CRS No: NISOC-CRS-BK-BK14-PEDCO-110-PI- PY -0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | یک درب نفر رو جهت واکنش در شرایط اضطراری با توجه به مسیرهای دسترسی لحاظ گردد. |  | 01/2294/401958 | 1401/10/21 | احتراما نقطه نظر با توجه به وضعیت توپوگرافی سایت اعمال گردید.
2 | جهت نهایی شازی موقعیت گودال سوخت حضور در محل و انجام بازدید میدانی ضروری است. شماتیک پیشنهادی شرکت گچساران جهت راهنمایی به پیوست ارسال می گردد. |  | 01/2294/401958 | 1401/10/21 | احتراما این چاه موجود بوده و موقعیت گودال سوخت مربوطه مشخص است.
3 | تعیین مسیر خطوط لوله مربوط به گودال سوزا و پساب طی بازدید میدانی و پس از مشخص شدن گودال سوزا و پساب میسر خواهد بود |  | 01/2294/401958 | 1401/10/21 | احتراما این چاه موجود بوده و موقعیت گودال سوخت و مسیر خطوط مربوطه مشخص است.
4 | محل جانمایی ساختمان برق مورد تایید نیست و راه دسترسی بدان وجود ندارد. |  | 01/2294/401958 | 21401/10/21 | احتراما جانمایی ساختمان برق اصلاح شد.
5 | محل جانمایی شلتر دیزل ژنراتور و مخزن سوخت آن مورد تایید نیست |  | BK-SUR-ENG-PIP-01-06415 | 1401/10/21 | احتراما جانمایی ساختمان ها به روز رسانی شد.
6 | محل ورود خط انتقال برق و نحوه دسترسی به ساختمان برق مشخص گردد. |  | BK-SUR-ENG-PIP-01-06415 | 1401/10/21 | احتراما نقطه نظر اعمال گردید. و نحوه دسترسی (ترنچهای مربوطه) در آخرین ویرایش اضافه می گردد.
7 | مساحت ساختمان های برق و نگهبانی و شلتر دیزل ژنراتور مطابق مدارک مهندسی پایه باشد. |  | BK-SUR-ENG-PIP-01-06415 | 1401/10/21 | احتراما نقطه نظر اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri/M.Karimi G.Khisravizadegan | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 17-Dec-2022 |  |  |  |  | Date: 17-Dec-2022