## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-TB-0005_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1416 |  |  | Transmital Date: 19 sep 2022
Document Title: TBE/TBA For Control Valves - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1416 |  |  | Transmital Date: 19 sep 2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-IN-TB-0005_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | پيرو جلسه برگزار شده در تاريخ 10/7/1401 موارد در صورتجلسه پيوست و همچنين فايل ضميمه اكسل (ديتاشيت) ارسال مي گردد. |  | BK-SUR-ENG-INS-01-05832 | 2022-10-03 | موارد ملاحظه گردیده و در نسخه جدید مدرک TBE و دیتاشیت اعمال گردید.
2 | با توجه به مغايرت و مشكلات بين مدارك وندورها، انتظار مي رود مدارك TBE پس از بررسي دقيق تر به عنوان مدرك نهايي ارائه گردد. |  | BK-SUR-ENG-INS-01-05832 | 2022-10-03 | ملاحظه گردیده و اعمال گردید.
3 | با توجه به اينكه مدارك پيش نياز اين مدرك، نهايي نمي باشد موارد در صورت تغيير به وندورها اعلام و در اين مدرك ديده شود. |  | BK-SUR-ENG-INS-01-05832 | 2022-10-03 | همانطور که کارفرمای محترم نیز استحضار دارند، مدرک دیتاشیت تایید گردیده و هرگونه تغییری در پروژه در هر صورت به وندور منتخب اعلام می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 3 Oct 2022 |  |  |  |  | Date: