## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-PR-DG-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1050 |  |  | Transmital Date: 6/7/2022
Document Title:Cause & Effect Diagram - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1050 |  |  | Transmital Date: 6/7/2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-PR-DG-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | اين مدرك مي بايست مطابق دياگرام هاي علت و معلول متداول، داراي هرعلت همراه با تگ مربوطه به همراه معلول مرتبط آن در نظر گرفته شود. |  | BK-SUR-ENG-PCS-01-04795 | 2022-06-21 | tag ها مطابق مدرک ESD Hierarchy اضافه گردید.
2 | اين مدرك با ESD Philosophy مربوطه مطابقت ندارد. |  | BK-SUR-ENG-PCS-01-04795 | 2022-06-21 | بررسی و اصلاح گردید.
3 | ليست مراجع به مدرك اضافه شود. |  | BK-SUR-ENG-PCS-01-04795 | 2022-06-21 | اعمال گردید.
4 | PB فعال كننده هر سطح توقف به همراه تگ مربوطه اضافه گردد. |  | BK-SUR-ENG-PCS-01-04795 | 2022-06-21 | tag ها مطابق مدرک ESD Hierarchy در نظر گرفته شده است.
5 | نحوه Deprssurizing ذكر شده در سطح صفر چگونه است و چه معلولي دارد؟ |  | BK-SUR-ENG-PCS-01-04795 | 2022-06-21 | با توجه به اینکه مدرک مذکور صرفا رابطه ی علت و معلولی Depressurizing را مطرح می کند و نحوه Depressurizing با توجه به اینکه کیسهای Despressurizing قبلا در طراحی سایت موجود در نظر گرفته شده است، لذا اطلاعات مدرک فوق می بایست در قالب سناریو پیش فرض موجود در سیستم ESD سایت در نظر گرفته شود.
6 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-04795 | 2022-06-21 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: