## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W046S-PEDCO-110-CV-PY-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1624 |  |  | Transmital Date: 28-Nov-2022
Document Title: General Civil Layout -W046S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-TR-1624 |  |  | Transmital Date: 28-Nov-2022
[5 empty] | CRS No: NISOC-CRS-BK-W046S-PEDCO-110-CV-PY-0001-D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در پاسخ به ردیف دو از Clarification by EPC Contractor مقتضی است به نامه شماره 324278 مورخ 1401/09/01 مراجعه شود. این موضوع کماکان به قوت خود باقی است |  | 01/2294/361967 | 1401/09/26 | گزارش ژئوتکنیک بر اساس اصلاحات مورد نظر کارفرما در حال ارسال می باشد.
2 | در پاسخ به ردیف چهار از Clarification by EPC Contractor و اظهارنظر آن پیمانکار اعلام می گردد که تبعات هرگونه تغییر بر عهده و مسئولیت آن شرکت بوده و کارفرما هیچ ادعایی را نمی پذیرد |  | 01/2294/361967 | 1401/09/26 | مورد قبول است.
3 | در پاسخ به ردیف 12 از Clarification by EPC Contractor همانگونه که پیشتر اعلام گردید مدرک Plot Plan مصوب برای تمامی چاه های دارای تلمبه یدک می بایست به تصویب برسد که تاکنون مستندات گفته شده دریافت نشده است. لذا بررسی این مدرک منوط به انجام این موضوع می باشد. |  | 01/2294/361967 | 1401/09/26 | نتایج بررسی مدل و Plot Plan که طی جلسات Model Review نهایی شده است و هم چنین موقعیت کلی محدوده ها که برای نقشه سیویل نیاز است در مدرک فعلی اعمال گردیده است. این صورتجلسه طی نامه شماره 01/2294/454510 مورخ 1401/11/30 ابلاغ شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: