## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-DG-0001_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1743 |  |  | Transmital Date: 31 Dec 2022
Document Title: Instrument Earthing Typical Diagram |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1743 |  |  | Transmital Date: 31 Dec 2022
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-IN-DG-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همان طور که در نامه 216168مورخ 1401/6/17 مطرح گردید: در بخش Notes ردیف 34 جهت ارت حفاظتی تجهیزات در سایت ، بدین صورت اصلاح شود در صورتی که مقاومت اهمی سیستم موجود از مقادیر مجاز بالاتر بود ضروری است ، جهت ارت حفاظتی الکتریکال در سایت ( محوطه توپک گیر) واحد تزریق گاز سیاهمکان سیستم ارتینگ مطابق استاندارد ایجاد خواد شد. |  | 01/2294/408715 | 1401/10/26 | نظر کارفرمای محترم بر روی مدرک اعمال گردید.
2
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: