## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W018S-PEDCO-110-PI-MR-0008_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0869 |  |  | Transmital Date: 27/Apr/2022
Document Title: PMR FOR STONE TRAP– W018S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0102-PI-TR-0869 |  |  | Transmital Date: 27/Apr/2022
[5 empty] | CRS No: PEDCO-CRS-BK-W018S-PEDCO-110-PI-MR-0008_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | عبارت " List of Documents Will be Finalized in Vendor Document index and Schedule" به عنوان نوت اضافه گردد. |  | BK-SUR-ENG-PIP-01-04122 | 02.05.2022 | احتراما در ویرایش D01 مدرک اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: J.Mousazadeh M. Torkaman | Signature |  |  |  | Clarified By: | Signature | M.Fakharian
| Date:02/05/2022 |  |  |  |  | A.Dabiri