## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-PY-0003_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1434 |  |  | Transmital Date: 24 Sep 2022
Document Title: Instrument Location Layout - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1434 |  |  | Transmital Date: 24 Sep 2022
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-IN-PY-0003_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | تجهیزات FT، PTو شیرهای کنترل به همراه لوازم جانبی نصب با توجه به هوک آپ نمایش داده شود. |  | 01/2294/298680 | 1401/08/16 | نحوه نصب و تجهیزات جانبی در مدرک Instrument Hook-up Diagram - Extension of Binak B/C Manifold به صورت کامل نمایش داده شده است و به دلیل ازدیاد داده در این مدرک نمایش داده نمیشود.لازم به ذکر است که این مدرک براساس مدل PDMS , Plot Plan تهیه شده است.
2 | تجهیزات TW نیز نمایش داده شود.(یا بصورت Note ذکر گردد) |  | 01/2294/298680 | 1401/08/16 | با توجه به نظر کارفرمای محترم، در قالب نوت به مدرک اضافه گردید.
3
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: